## Project_ndg v2.0
CMC NDG Next - C-App Effort Estimation
Hybrid App (iOS + Android) + Admin Panel
WBS ID | Feature Name | Feature Reference | What It Does and Offline Notes | Total Hours | Total SP | Phase
1. LOGIN & USER ACCOUNT
1.1 | Login Screen | F-01 | Sign-in page with username, password, and the car brand's logo. When the app opens, users see a clean sign-in screen. The logo, colors, and app name automatically reflect the car manufacturer's branding |  |  | MVP
1.2 | Log In with Automaker Authenticator (IDP) | F-02 | Connect to the automaker's existing login system — no separate account needed. Users sign in with their existing car brand account (e.g., My Nissan). The app securely passes the credentials to the brand's identity system and receives a digital key (token) to keep the session active. Offline: If the user was previously logged in, the saved token lets them reopen the app without re-entering credentials. |  |  | MVP
1.3 | User Profile and Preferences | F-52 | Store the user's language choice, choosen vehicles model, and app settings. CMC only stores what is needed for the app to work: language preference, linked vehicle IDs, usage activity, and display settings. Personal identity data stays with the car brand. |  |  | Phase 1
1.4 | Data Privacy and Consent (GDPR) | F-52 | Let users review, agree to, and withdraw their data permissions. At sign-up, users agree to how their data will be used. They can revisit or withdraw consent at any time from Settings. Users can request full deletion of all CMC-held data, in line with GDPR. |  |  | Phase 1
1.5 | Password Reset and Session Handling | F-01 | Forgot password flow and managing logged-in sessions across devices. Users receive a reset link by email. Sessions are managed per device. When a password is changed, all other devices are logged out automatically for security. |  |  | MVP
2. VEHICLE SELECTION
2.1 | Choose Your Vehicle Model | F-03 | After login, pick from a list of available vehicle models. The list shows models available for the user's car brand.It is managed by the admin — no app version update is required to add or remove models, and these changes can only be configured from the admin panel. |  |  | MVP
2.2 | Choose Model Year | F-04 | Pick the production year of the selected vehicle. After choosing a model, the user selects the year (e.g., 2024, 2025, 2026). This determines which version of the manual, FAQs, and all features the user will see. |  |  | MVP
2.3 | Save and Manage Multiple Vehicles | F-03, F-05, F-49 | Households with two or more cars can register and switch between vehicles. Each vehicle has its own separate manual, chat history, notifications, and app's feature usage progress data. Users can switch vehicles at any time. |  |  | MVP
2.4 | Home Screen After Vehicle Selection | F-06 | After confirming the model and year, open the home screen with the full app. Once confirmed, the home screen loads with the bottom tab bar (Home, Chat, Manual, Notifications, Status). All content is tailored to the chosen vehicle and year. |  |  | MVP
3. OWNER'S MANUAL VIEWER
3.1 | Manual Entry Buttons on Home Screen | F-07 | Home screen buttons to browse the manual in-app or download the PDF. Two buttons let users open the manual viewer or save the PDF. Download status is shown (e.g., Saved for offline). Offline: manual in-app button will be visible. The in-app manual and open immediately without internet. |  |  | MVP
3.2 | Browse Manual In-App (HTML Viewer) | F-08 | Read the complete vehicle manual inside the app — chapters, images, and easy navigation. Displayed as clean, readable content with a table of contents, in-manual search, and scroll memory so users return to where they left off. There should be a search box in top of manual viewer. Offline: The full manual is downloaded on first use. All chapters, images, and navigation work completely without internet. |  |  | MVP
3.3 | Show the Right Manual for Each Vehicle | F-09 | Automatically load the correct manual when the vehicle is selected or changed. Switching vehicles immediately updates the manual, FAQs, and all content to match the active vehicle. No manual switching is needed by the user. |  |  | MVP
3.4 | Jump Directly to a Manual Chapter (Deep Link) | F-08 | Open the manual scrolled to the exact section referenced by a chatbot answer or notification. Tapping a manual link opens the viewer at that precise chapter and heading. Offline: Deep links into cached manual chapters work with no internet connection. |  |  | MVP
3.5 | External Link Management & Rendering | F-10 | Support rendering and launching external links provided through CMS or backend configuration, including videos, official websites, support pages, map locations, or phone call actions based on the content context. Users can tap an external link card or button from Home or Chat, after which the app validates the link type and opens the appropriate browser, video player, map application, or phone dialer. The feature uses external URLs, content type metadata, display labels, phone numbers, and deep link configurations to provide seamless access to support, promotional, and informational resources. |  |  | Phase 1
4. AI CHATBOT
4.1 | Chat Screen Layout | F-14 | A clean messaging screen with conversation bubbles, typing input, and a send button. Works like a familiar messaging app. Supports text responses, images responses, tappable action buttons, and a typing indicator while the AI prepares its answer. Offline: In offline this feature will be disable with a tooltip note |  |  | MVP
4.2 | Save Chat History | F-14 | Keep all past conversations stored per vehicle. Chat history persists across app restarts and is linked to the active vehicle. Users can delete (soft delete) individual messages or their entire history. |  |  | MVP
4.3 | Home Search Goes to Chat | F-11, F-18 | The home screen search bar is a shortcut into chat. When the user searches, the app opens Chat with the question entered and the AI response loading below. Typing a question in the home screen search bar opens chat with the query ready. Offline: In offline this feature will be disable with a tooltip note |  |  | Phase 1
4.4 | Frequently Asked Questions (FAQ) | F-12, F-13 | Show 3 rotating suggested questions on the home screen; tapping opens the relevant manual section. FAQ suggestions refresh each visit. Offline: The full FAQ dataset is saved on the device. All questions and their manual links are fully accessible without internet. |  |  | MVP
4.5 | Quick Question Buttons in Chat | F-13 | Pre-made question chips in chat that users tap to ask instantly. Buttons like 'How do I pair Bluetooth?' appear in chat. Tapping one automatically sends the question and loads the AI answer. Labels are managed by the admin. |  |  | MVP
4.6 | AI-Powered Text Answers | F-16 | The chatbot answers any question typed in plain language. Users ask anything about their vehicle and receive a sourced answer with a link to the relevant manual chapter. Offline: The app matches the query against saved FAQ answers and shows the closest match, with a note that full AI responses require internet. |  |  | MVP
4.7 | Welcome Message and Quick Start | F-15 | A friendly opening message when chat is first opened, with quick-reply buttons. The chat opens with a welcome message and quick-reply buttons for common topics. Varies by vehicle and language, managed by the admin. Offline: Loads from saved app configuration. |  |  | MVP
4.8 | Helpful / Not Helpful Rating | F-25, F-29 | Thumbs up / down on every chatbot response to improve answer quality over time. Every AI answer has a rating button. Ratings feed into admin analytics and the content improvement process. Offline: Ratings are saved locally and synced to the server when the device is back online. |  |  | MVP
4.9 | In-App Customer Support Handoff | F-114 | When the chatbot cannot resolve an issue, users can escalate to support directly from the app. The chatbot suggests contacting support, and upon user confirmation, the app creates a support case with relevant context such as chat history, searched terms, vehicle details, and troubleshooting steps, then submits it to the support system and returns a case reference. This reduces repetition for users and allows support agents to continue the conversation with full context. |  |  | Phase 2
5. STEP-BY-STEP TROUBLESHOOTING
5.1 | Guided Problem-Solving Flows (T1-T6) | F-17 | Chatbot asks follow-up questions to diagnose an issue and provide a step-by-step fix. When a user describes a problem, the chatbot asks targeted questions to identify the exact issue, then provides a clear fix with images and manual links. Covers 6 common problem areas. Offline: Diagnostic trees are saved on the device and run locally |  |  | MVP
5.2 | Warning Lamp Identification in Chat | F-19 | User taps the warning lamp they see on their dashboard; chatbot explains what it means. A visual grid of all warning lamp icons appears in chat. The user taps the matching icon; the chatbot responds with the meaning, urgency level, and recommended action. |  |  | Phase 1
5.3 | Visual Step-by-Step Pop-up Guide | F-20 | For complex tasks, a swipeable guide with images opens as a pop-up over the chat. Some features need more than text to explain. The chatbot triggers a step-by-step overlay with an image per step. Users swipe through at their own pace. |  |  | MVP
6. WARNING LIGHTS
6.1 | Warning Lights Icon Grid | Not in FR, came from mockup-WL-Grid | A searchable screen showing all dashboard warning light icons grouped by urgency color. Icons grouped by color (Red = stop, Amber = caution, Green = info, Blue = status). Users can search by name. Offline: Complete warning lights index is saved on the device — a priority for driver safety in remote areas. |  |  | MVP
6.2 | Warning Light Detail and Description | Not in FR, came from mockup-WL-Article | Tap any icon to read the full explanation with urgency level and what action to take. Tapping opens the article: what the light means, urgency, and step-by-step action. Offline: All warning light articles are pre-saved on the device. User can look up any dashboard warning with no mobile signal. |  |  | MVP
7. SMART NOTIFICATIONS
7.1 | Notification Centre Screen | F-28 | All notifications in one place, grouped by type and date, per vehicle. Shows tips, maintenance alerts, and feature suggestions. Every notification shows which vehicle it relates to. Offline: All previously received notifications are fully readable offline. Manual links open the cached manual. |  |  | MVP
7.2 | Rate a Notification (Helpful / Not) | F-29 | Thumbs up / down on each notification to improve future delivery. Negative ratings stop that notification type and feed into admin reports. Offline: Ratings are saved locally and synced when back online. |  |  | MVP
7.3 | Unread Notification Badge | F-30 | A red number badge on the Notifications tab showing how many unread items there are. Badge count is per vehicle. It resets when the user opens the notification screen. |  |  | Phase 1
7.4 | Deliver Notifications to iOS and Android (Push) | F-31 | Send push notifications to users' phones via Apple (APNs) and Google (FCM). Handles all app states: open (in-app banner), in background, or closed (system notification). Users can turn notification categories on/off. |  |  | MVP
7.5 | Smart Alert Cards on Home Screen | F-23, F-26 | Contextual tip cards on the home screen based on time, season, or the user's stage. A rotating card shows timely tips (e.g., cold weather advice in winter, basic setup in the first week). Card content is authored in the admin panel. Offline: The most recently fetched card is cached and shown offline. |  |  | MVP
7.6 | Alert Detail Screen | F-24 | Full-detail view when a user taps an alert or smart card. Opens a detail screen with the full explanation, images, and action buttons (Open Manual, Try this feature, Dismiss). Manual links open the relevant chapter. |  |  | MVP
7.7 | Notification Rules Engine | F-31, F-32, F-33 | The engine that decides which notification to send, to whom, and when. Admins configure rules based on three trigger types: user's situation (time of day, weather), ownership milestones (days since registration), and feature usage gaps. When conditions are met, the notification is queued and delivered. |  |  | MVP
7.8 | Weather and Situation Data for Notifications | F-31, F-35 | Connect to weather and location data to power real-time situation-based tips. Pulls live weather and time-of-day context to trigger relevant alerts — e.g., ice warnings in freezing temperatures, lighting tips at night. Requires location permission. Offline: In offline this feature will be disable with a tooltip note |  |  | MVP
7.9 | Ownership Milestone Notifications | F-32, F-36 | Send the right tips at the right stage of vehicle ownership. Tracks how long the user has owned the vehicle and sends stage-appropriate content: basic setup in week 1, feature discovery in month 1, maintenance reminders at 6 months. |  |  | MVP
7.10 | Feature Usage Tracking for Recommendations | F-33, F-37 | Track which app and vehicle features users have explored to suggest what they have not tried. Features that most similar users have explored — but this user has not — are flagged as recommendations. Drives personalized notifications and FAQ suggestions. |  |  | Phase 2
7.11 | Notification Frequency Limits and Quiet Hours | Not in FR, came from mockup | Prevent notification overload with daily limits and do-not-disturb settings. Configurable limits cap daily notifications (e.g., max 2 per day). Quiet hours (e.g., 10 PM – 7 AM) are respected. Advanced tips are held back until basic features have been explored. |  |  | Phase 2
8. DISCOVER YOUR VEHICLE AND RECOMMENDATIONS
8.1 | Discover Your Vehicle Features | Not in FR, came from mockup-Discover | A curated guide to the best features of the vehicle, grouped by category, with manual links. Shows categorized highlights (safety, comfort, technology) for the user's specific vehicle. Reading features adds to the user's progress level. Offline: The features list is saved on the device. Browsing and opening manual links work fully without internet. |  |  | Phase 1
8.2 | Weather-Based AI Driving Tips | F-35, F-36 | Generate real-time driving tips based on the user's current weather conditions. The app fetches local weather and uses AI to generate relevant vehicle tips from the manual. Tips include a link to the relevant manual chapter. Requires internet connection. Offline: In offline this feature will be disable with a tooltip note |  |  | Phase 2
9. USER PROGRESS AND GAMIFICATION
9.1 | User Knowledge Level and Progress Bar | F-38, F-39, F-40 | Track how much the user has explored; show their knowledge level with a progress bar. Users advance through levels as they browse the manual, ask questions, and use features: Getting Started, Learner, Smart Driver, and Expert. |  |  | MVP
9.2 | Achievement Badges & Usage Tracking | F-44, Badges | Earn badges for reaching milestones in how the app is used, while gaining points and leveling up through user activity updates. Users unlock badges for activities like sending the first chat message, reading multiple chapters, and completing step guides. Points and levels are automatically updated in response to user events, and locked badges appear greyed out to encourage completion. |  |  | MVP
9.3 | Maintenance Reminder Tracker | Not in FR, came from mockup-Maintenance | A simple tool to record and track the next scheduled vehicle service. Users enter when their next service is due. The app keeps a summary. Offline: Fully works offline. All data is stored only on the device. |  |  | Phase 2
9.4 | Driving Data Display | F-41 | Display driving-related analytics such as mileage, distance travelled, fuel economy, and sync status. Mileage and driving activity contribute to points, progression, and level-up calculations. |  |  | Phase 1
9.5 | Feature Utilisation & Recommendation Tracking | F-42 | Track explored vehicle features and usage coverage from the app while adapting recommendations and content suggestions based on user interaction history. |  |  | MVP
9.6 | Manual Maintenance Plan Entry | F-43 | Provide a manual maintenance entry screen where users can set service intervals by time or mileage. Users can open the Status tab → Maintenance Plan, enter the next service interval, target mileage, and optional current odometer reading, then view the calculated maintenance summary and next expected service status. The system uses service interval values, mileage thresholds, current odometer, and manual maintenance plans to enable maintenance tracking before telematics integration, allowing users to start monitoring service schedules immediately after onboarding. |  |  | MVP
10. SETTINGS AND ACCESSIBILITY
10.1 | Settings Screen | F-49 | Central screen for all user preferences, clearly organized by category. Sections for: Language, My Vehicles, Display, Accessibility, About App, and Account. Offline: The settings screen and all toggles work fully without internet. |  |  | MVP
10.2 | Choose App Language | F-45, F-46, F-47, F-48 | Switch the entire app into Japanese, English, French, or Spanish. When the user changes language, every part of the app switches: menus, chatbot responses, FAQ, notifications, and manual content. The selection is saved and persists across sessions. |  |  | MVP
10.3 | Dark Mode and Display Theme | Not in FR | Switch between light (white background) and dark display modes. A simple toggle in Settings. The choice is saved and applied across the entire app immediately. |  |  | MVP
10.4 | Accessibility Options | F-116 | Make the app easier to read and use for all users. Users can increase text size, turn on high contrast mode, and enable reduce motion to stop animations. All settings are saved globally. |  |  | Phase 2
10.5 | Screen Reader and Accessible Feedback | F-117, F-118 | Full support for iOS VoiceOver and Android TalkBack screen readers. Every button, icon, and state change has a descriptive label. Status never relies on color alone — ensures usability for color-blind users. |  |  | Phase 1
11. ADMIN PANEL
11.1 | Admin Panel and Login | F-52, F-53, F-54 | The web-based admin tool's main frame with login and role-based navigation. Admins log into a web application. The sidebar menu shows only permitted sections based on role. A brand switcher lets system admins manage multiple car brands from one login. |  |  | MVP
11.2 | Manage Content (Manuals, FAQ, Step Guides, Features) | Not in FR, came from mockup-FAQMgmt, FeatureList | Create, edit, review, and publish all in-app content from one place. Covers manuals, FAQ entries, step-by-step guides, and vehicle feature highlights. Content goes through a Draft, Review, Publish workflow. Full version history is maintained. |  |  | MVP
11.3 | Manage Users and Assign Roles | F-52, F-53, F-54 | View, search, and manage all app users, their roles, and access levels. Admins can search users, view profile and usage history, assign or change roles, enable or disable accounts, and review a full audit log of every action. |  |  | Phase 1
11.4 | Build and Configure Notification Rules | Not in FR, came from mockup-NotifMgmt | A visual form for setting up when and what to send as notifications. Admins choose a trigger type, set conditions, select a notification template, and set the target audience. Rules can be toggled on/off instantly. A test mode previews affected users before activating. |  |  | MVP
11.5 | Analytics and Usage Reports | F-111, F-112, F-113 | Charts and reports showing how users interact with the app. Shows: most common questions, chat resolution rates, average turns to resolve an issue, drop-off points, and notification engagement rates. Filterable by date, vehicle model, and language. Exportable to CSV. |  |  | Phase 2
11.6 | Brand and App Configuration | Not in FR, came from mockup | Per-brand settings: logo, colors, login provider, available languages, and feature switches. Each car brand gets its own configuration: branding assets, authentication method, available languages, vehicle catalog, and feature toggles. |  |  | Phase 1
11.7 | Multilingual Content System (i18n Framework) | F-47, F-48 | Framework that makes every part of the app fully translatable without code changes. All app text is stored as labeled keys. Adding a new language only requires adding a translation file — no code release needed. |  |  | MVP
11.6 | User Roles and Access Levels | F-53, F-54 | Control who can do what in the app and in the admin panel. Regular users see only their own data. Content editors can update manuals and FAQs. Business admins manage the full system. Permissions are applied automatically — a user can never access data beyond their role. |  |  | Phase 1
11.7 | Admin: Upload and Manage Manuals | Not in FR-Need for data processing | Admin tool for uploading, processing, and publishing vehicle manuals. Upload manual files through IOM CMS into s3 bucket. The system processes them from s3 bucket directly into chapters, images, and warning light data, tagged to the correct vehicle model, year, and language. |  |  | MVP
11.8 | Driving Data Source Configuration | F-41 | Allow administrators to configure and manage the vehicle data source, telemetry mappings, synchronization settings, and API connection details required for driving analytics and gamification tracking. |  |  | Phase 1
11.9 | CS Case Handoff Configuration & Management | F-114 | Provide an admin interface to manage customer support handoff settings, including routing rules, escalation triggers, and support system integrations. Admins can configure how unresolved chatbot conversations are routed, what information is shared with support teams, and which external CRM or helpdesk systems are used. This ensures support requests are sent to the correct teams with the necessary context. |  |  | Phase 2
12. API HUB AND EXTERNAL CONNECTIONS
12.1 | API Hub Core (MCP Server) | F-119 | A central hub that lets the AI chatbot connect to external tools and data sources. Handles all AI-to-external-system calls, routes requests, formats responses, and logs every interaction. Includes health checks and retry logic. |  |  | Phase 1
12.2 | Register and Manage External Tools | F-120 | Admin interface to add, configure, and monitor connected external tools. Admins register new connections (name, API endpoint, authentication, input/output format). Each tool can be enabled or disabled instantly. Includes availability scheduling. |  |  | Phase 1
12.3 | Access Control for API Hub | F-121 | Ensure only the right users and tools can access each external connection. Every API hub call is checked at three levels: which user is requesting, which app is calling, and which tool is being invoked. Full audit trail of all access. |  |  | Phase 1
12.4 | Connect to Content System (CMS) | F-122 | Allow the chatbot to retrieve up-to-date FAQ answers and manual content from the CMS. Real-time content retrieval with authentication, data mapping, and caching strategy. |  |  | Phase 1
12.5 | Connect to Brand's Official Website | F-122 | Let the chatbot reference product information from the automaker's official website. The chatbot can retrieve product pages, feature descriptions, and support URLs from the brand's website as an additional knowledge source. |  |  | Phase 1
12.6 | Connect to Logging System | F-122 | Forward all AI interaction logs to the central logging platform. Every AI call is logged with a trace ID for end-to-end debugging with configurable severity levels and reliable delivery. |  |  | Phase 1
12.7 | Connect to Notification Delivery Service | F-122 | Send push notifications through the delivery platform using the API hub. Includes delivery status tracking, automatic retry on failure, and message template rendering before send. |  |  | Phase 1
12.8 | Error Handling and Fallback for Failed Calls | F-123 | Graceful recovery when any external connection fails. 4-step chain: retry the call, return a pre-set fallback answer, offer handoff to human support, fall back to AI general knowledge. Each tool has its own retry and timeout configuration. |  |  | Phase 1
12.9 | Dealer Locator (Phase 3) | F-60 | Show nearby dealerships on a map with contact details. Users find the nearest dealer on a map with address, phone, and opening hours. Uses GPS for closest location. Includes tap-to-call and tap-to-navigate shortcuts. |  |  | Phase 3
12.10 | Customer Support Handoff Interface (Phase 3) | F-59 | Framework to pass unresolved chats to a human support agent. When the chatbot cannot resolve an issue, the full conversation context is passed to the human support team. The interface contract is defined now; the actual CS system connection is confirmed in Phase 3. |  |  | Phase 3
13. AI AND LANGUAGE MODEL MANAGEMENT
13.1 | AI Chat Engine Integration | F-22 | Connect the chatbot to the AI language model and manage how questions are answered. The backend service assembles a prompt (user question + relevant manual content + chat history), sends it to the AI model, and formats the response for the chat screen. Includes guardrails to keep the AI focused on vehicle topics. |  |  | Phase 1
13.2 | AI Model Settings and Tracking (Admin) | Not in FR, came from mockup-LLMMgmt | Admin screen to configure the active AI model, its instructions, and view change history. Admins select which AI provider and model version is active, update the system instructions, and view a full history of model changes for accountability. |  |  | Phase 2
14. APP PERFORMANCE MONITORING
14.1 | AI Response Quality Tracking | F-55 | Log every AI call with speed, cost, and user rating for admin review. A complete record is kept for every AI interaction: question, response, timing, model used, token cost, and user's rating. Admins can search and filter traces to debug issues. |  |  | Phase 1
14.2 | AI Performance Dashboard (Admin) | Not in FR | Admin charts for AI quality: speed, error rate, satisfaction score, and cost. Shows live metrics: total AI requests per day, average response time, error rate, user satisfaction score, and estimated daily AI cost. Supports side-by-side comparison of two model versions. |  |  | Phase 1
14.3 | App Health Monitoring and Alerts | Not in FR | Monitor the app's backend services and alert the team automatically if something goes wrong. Every API endpoint is monitored for uptime and response time. If error rates exceed a threshold or a service goes down, an automatic alert is sent to the engineering team. |  |  | Phase 1
15. IN-APP FEEDBACK AND VOICE OF CUSTOMER
15.1 | In-App Feedback Collection | Not in FR, came from mockup-Feedback | A feedback button in Settings where users can share issues or suggestions. Users can rate the app and leave written feedback. Thumbs up/down throughout the app all feed into this system. Offline: Feedback is saved locally and sent when internet is restored. |  |  | Phase 2
15.2 | Feedback Reports and Content Improvement (Admin) | F-111, F-112, F-115 | Admin view of feedback data with tools to track and act on content improvements. Admins see aggregated feedback, low-rated answers, frequently unanswered questions, and drop-off patterns. They can create improvement tasks from feedback data and track resolution. |  |  | Phase 2
16. MOBILE APP TECHNICAL SETUP
16.1 | Mobile App Framework and Navigation | Not in FR- Need for project structure | The foundational structure of the hybrid mobile app for iOS and Android. Sets up the cross-platform app: tab bar navigation, screen routing, deep links, branded splash screen, and app lifecycle management. |  |  | MVP
16.2 | Offline Data Storage and Cache Sync System | F-50 | Save the full manual, FAQs, and settings on-device; sync updated content automatically when back online. On first vehicle selection (online), the app downloads the full content package (~5-15 MB) to the device. A lightweight version check on every app open downloads only changed sections. Content older than 7 days shows a refresh banner. Ratings and events made offline are queued and synced when connectivity returns. |  |  | Phase 1
16.3 | Push Notification Device Setup | Not in FR- Need for project structure | Register the user's device for push notifications with Apple and Google. Sets up push registration for iOS (APNs) and Android (FCM). Handles all delivery states. Tapping a notification routes the user to the relevant screen. |  |  | Phase 1
16.4 | App Speed and Performance Optimization | Not in FR- Need for project structure | Ensure fast loading, smooth scrolling, and efficient use of phone memory. Compresses and lazy-loads images, uses list virtualization for long scrollable screens, manages memory to prevent crashes on lower-end phones, and ensures the first screen appears within 2-3 seconds. |  |  | Phase 3
16.5 | App Store Submission (iOS and Android) | Not in FR- Need for project structure | Prepare and submit the app to the Apple App Store and Google Play Store. Covers app store listing (name, description, screenshots), privacy policy, compliance with Apple and Google review guidelines, code signing certificates, and final build submission. Scoped up to UAT release. |  |  | MVP
16.6 | Multi-Tenant Application Structuring | Not in FR- Need for project structure | Design and implement a multi-tenant application architecture to support multiple organizations, brands, or client environments within the same platform. Covers tenant isolation, tenant-specific configuration, branding support, environment separation, scalable data structure, role/access segregation, and tenant-aware APIs/services. Includes foundational backend and frontend structuring required before tenant onboarding and enterprise customization. |  |  | MVP
17. CLOUD INFRASTRUCTURE AND SECURITY
17.1 | API Server and Request Handling Setup | Not in FR- Need for project structure | Set up the API gateway that processes all requests from the app and admin panel. Configures rate limiting, request validation, cross-domain settings for the admin panel, consistent error formatting, and multi-tenant routing. |  |  | MVP
17.2 | Cloud Infrastructure Setup | Not in FR- Need for project structure | Provision all servers, databases, file storage, and networking in the cloud (AWS). Sets up compute servers, managed database (PostgreSQL), object storage for PDFs and media, CDN for fast global delivery, networking, SSL certificates, and DNS for all endpoints. |  |  | MVP
17.3 | Security and Data Protection | Not in FR- Need for project structure | Protect the app against common security threats and store sensitive data safely. Sanitizes all inputs, applies XSS protection headers, adds login rate limiting to block brute-force attempts, stores API keys in a secrets manager, and runs regular dependency audits. |  |  | Phase 1
17.4 | Centralized Logging and Error Alerts | Not in FR- Need for project structure | All system logs in one searchable place with automatic error notifications to the team. Every system component writes structured logs to a central platform. An error tracking service captures unhandled exceptions. Log retention rules balance cost and compliance requirements. |  |  | MVP
17.5 | System hardening | Not in FR- Need for project structure | Overall system performance tuning to ensure a smooth app experience |  |  | MVP
18. Application Architecture design support from BS23 | [5 empty] | MVP
19. Backend Mockup | [5 empty] | MVP
20. UAT Feedback, Resulation and Minor Enhancement | [5 empty] | MVP & P1-P3
21. Project management support |  | BS |  |  |  | MVP & P1-P3
|  | Sakai |  |  |  | MVP & P1-P3 | 12 weeks x 0.5
|  | Enomoto |  |  |  | MVP & P1-P3 | 12 weeks x 0.5
|  | Matsumoto |  |  |  | MVP & P1-P3 | 12 weeks x 0.5
22. Project technical documentation and Application User Manual | [5 empty] | MVP & P1-P3
Functional development |  | MVP |  | 1209.7 | 151.2125
Functional development |  | Phase 1 |  | 566.8 | 70.85
Functional development |  | Phase 2 |  | 180.7 | 22.5875
Functional development |  | Phase 3 |  | 58.5 | 7.3125
Management |  | BS |  | 504 | 63
|  | RE |  | 576 | 30
TOTAL DEVELOPMENT EFFORT |  |  |  | 2519.7 | 314.9625
GRAND TOTAL STORY POINTS (1 SP = 8 hrs) |  |  |  |  | 315
ASSUMPTIONS
1. The mobile app is built as a hybrid app (one codebase for both iOS and Android).
2. The admin panel is a web-based application.
3. Phase 1 baseline uses English (EN). The i18n framework supports Japanese, French, and Spanish rollout in subsequent phases.
4. CMC will supply all content: vehicle manuals, FAQs, step guides, diagnostic flows, and notification templates.
5. Data ownership split: the car brand holds personal identity data (name, contact); CMC holds only app-specific supplementary data (language, vehicles, usage logs, gamification status).
6. Cloud infrastructure will be hosted on AWS.
7. Diagnostic flows cover 2-3 topics for Phase 1 (e.g., Bluetooth pairing, warning lamps); content authored by CMC.
8. API Hub Phase 1 includes 4 connectors: CMS, brand website, logging platform, and notification delivery service.
9. App Store submission (iOS App Store + Google Play) is in scope up to UAT launch.
10. All third-party service license costs (AI model API, push notification services, cloud services) are carried by CMCG.
11. CMC provides visual mockups and design assets by mid-May 2026.
12. Offline cache covers: complete HTML manual, warning lights, FAQ dataset, and diagnostic trees. Cache TTL is 7 days (configurable); version is checked silently on every app open when online.

## Timeline
Project C-App
Project Timeline
Particular/Task | Responsible Team | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
Milestone-1 | BS23 | Week 1: MVP
Milestone-2 | BS23 | Week 7: Phase -1
Milestone-3 | BS23 | Week 9: Phase-2
Milestone-4 | BS23 | Week 10: Phase-3
Milestone-5 | BS23 | Week 10: MVP , P1-P3 (WBS#20,21,22)
Development Cycle 1 | BS23 | bar: Week 1 to Week 3
Client Demo, Feedback & Modification | BS23 and Client | bar: Week 3
Development Cycle 2 | BS23 | bar: Week 4 to Week 6
Client Demo, Feedback & Modification | BS23 and Client | bar: Week 6
Development Cycle 3 | BS23 | bar: Week 7 to Week 9
Client Demo, Feedback & Modification | BS23 and Client | bar: Week 9
Development Cycle 4 | BS23 | [14 empty] | ` | bar: Week 10 to Week 12
Client Demo, Feedback & Modification | BS23 and Client | bar: Week 12
Final UAT | BS23 and Client | bar: Week 13
Production Release | BS23 and Client | bar: Week 14